MalariAI — Co-Author Task Assignment

Mohammed Ali  •  May 2026  •  Confidential

From: Kaysarul Anas Apurba (KB)  •  Laurentian University, Canada

# 1. Context & Role Division

The MalariAI paper is progressing in phases. I (KB) am completing all coding work — Phase 1 (EDA) is done, Phase 2 (Faster R-CNN baseline) is in progress, and Phase 3 (Watershed + EfficientNet pipeline) will follow. Your role is paper writing, literature verification, and figure preparation. I am not expecting you to run any code. When I have experimental results ready I will share the numbers with you directly so you can write up the analysis.

I am currently finishing another paper (Scale Laws in Scientific RAG) for arXiv submission in the next 2–3 days. Once that is submitted, I will move full-time to MalariAI and run Phase 2 and Phase 3 experiments on Kaggle. That means I need the literature extraction work done before I come back to this, so we are not bottlenecked.

# 2. Immediate Tasks (Due Before I Return to MalariAI)

These tasks do not require me or my code. You can start immediately.

## Task 1 — Paper Extraction Tables (Papers 1–4)

The co-author reading guide is in paper_writing/coauthor_reading_guide.md. It has a detailed extraction table for each of the four reference papers. Fill in every row for each paper. This is not a summary — I need exact numbers, exact quotes, exact metric names from the PDFs.

- Papers are in the paper_writing/ folder (PDFs 1–4)

- Paper 4 (Pandiaraj et al.) has already been read by me — still verify and fill in the table to confirm my notes are accurate

- Pay special attention to: exact future work quotes (we cite these as gap evidence), whether mAP or just accuracy is reported, and whether XAI or overlap handling is mentioned

Deadline: 1 week from today

## Task 2 — Related Work §2 Prose Revision

Once the extraction tables are done, open MalariAI_Paper_Draft.tex and go to \subsection{Summary of Limitations} (Table 1) and the five Related Work subsections (§2.1–§2.6). Verify the prose matches your extraction findings. Flag anything that looks wrong with a %% COAUTHOR NOTE: comment above the line. Do not rewrite sections — just mark discrepancies.

- Do NOT compile the .tex to PDF — leave that to me

- Fix bibliography placeholders: singh2025, loh2021, delgado2020 BibTeX entries need full author details

Deadline: 2 weeks from today

## Task 3 — Introduction & Conclusion Drafts

These two sections are listed as your responsibility in the paper status table. You do not need experimental results to draft these — the Introduction can be written from the problem statement and related work, and the Conclusion can be a forward-looking draft that I will fill with actual numbers later.

- Introduction: Frame the three problems (P1, P2, P3) and state the contributions. Draft based on the README abstract and problem_statement.md

- Conclusion: 1 paragraph summary of approach + 1 paragraph future work. Use placeholders like [INSERT mAP RESULT] where numbers go

Deadline: 3 weeks from today

# 3. Full Collaboration Timeline

This is the projected schedule. Dates will adjust once I confirm Phase 3 experiment results.

| Deliverable | Deadline | Notes |
| --- | --- | --- |
| Extraction tables (Papers 1–4) | Week 1 | Your immediate priority. See coauthor_reading_guide.md |
| Related Work §2 verified + annotated | Week 2 | Markup discrepancies in .tex with %% COAUTHOR NOTE |
| Introduction draft | Week 3 | Use placeholders for results; frame P1/P2/P3 |
| Conclusion draft | Week 3 | Forward-looking; placeholders for numbers |
| KB: Phase 2 (Faster R-CNN) complete | Week 2–3 | I will send you the baseline mAP table when done |
| KB: Phase 3 (Pipeline B) complete | Week 4–5 | I will send you Stage 1 + Stage 2 numbers |
| Architecture figure for Pipeline B | Week 5 | After I confirm Stage 1 watershed output visually |
| Results §4 analysis written | Week 6 | After I share all experiment numbers with you |
| Full review pass | Week 7 | Both of us — I will tag you when draft is complete |
| arXiv submission | Week 8 | Target: end of July 2026 |

# 4. What You Do NOT Need to Do

- Run any code, notebooks, or experiments — all of that is on me

- Download or set up the BBBC041 dataset

- Touch Phase 2, Phase 3, or Phase 4 folders

- Compile the .tex to PDF at any point

- Write the Methods section (§3) — that is mine; I write it from the code

# 5. Communication

Please send me a quick message when you start and when you finish each task so I can track progress. If anything is unclear in the extraction tables or the .tex, just ask — do not guess.

KB email: kapurba@laurentian.ca

Thank you — your contribution to this paper is valued and I want us to submit something we are both proud of.